# Proposal: Hosting Plan for the LHB Member Management System (LMMS)

Prepared by: [Your Name], IT Department

Date: 14 July 2026

For: Management Review & Approval

## 1. Executive Summary

LMMS is the new internal staff application replacing our legacy Informix system, managing

~32,000 members, ~34,000 timeshare agreements, and AMC billing. Development is on track for

completion around July 2027.

To deploy the system for user acceptance testing (UAT) now and for live production later, we

require a proper hosting environment. Our current test setup — an ordinary desktop PC (Windows 10,

8 GB RAM, 256 GB disk) — is inadequate and cannot serve as a production or long-term test platform.

After evaluating three options (cloud VPS, serverless platform, and on-premise server), we

recommend a phased approach:

Phase 1 (now – go-live): Host development/UAT on a low-cost cloud VPS (~RM28–116/month).

Phase 2 (at go-live, ~2027): Decide between a dedicated on-premise server or continuing on

the VPS, based on the system's actual, proven resource requirements.

This avoids committing capital to hardware before requirements are finalised, while giving us a

proper hosted environment immediately at minimal cost.

Approval requested: authorisation to proceed with Phase 1 (a monthly VPS subscription, starting

at approximately RM28/month).

## 2. Background & Current Situation

| Item | Status |
| --- | --- |
| Application | LMMS — Node.js + PostgreSQL, internal web application |
| Users | All internal staff (accessed over the company network) |
| Current test environment | A desktop PC (Windows 10, 8 GB RAM, 256 GB) — underpowered, not a proper server |
| IT support | In-house IT staff available |
| Existing server infrastructure | None |
| Target completion | ~July 2027 |

As the system's modules expand, we will need a properly specified, reliable environment for both

testing and production.

## 3. Options Evaluated

### Option A — Cloud VPS (Recommended for Phase 1)

A rented virtual private server (Windows), running the application exactly as built. Provider

reviewed: Shinjiru Technology (Malaysian). No code changes required; matches our current setup.

### Option B — On-Premise Server (Candidate for Phase 2)

Purchase a dedicated physical server hosting two virtual machines — one for Production, one for

Testing. Keeps all member data fully in-house and delivers network-speed access for internal users.

### Option C — Serverless Platform (Vercel) — Not Suitable

Evaluated and rejected. Vercel is designed for public websites, not long-running internal business

applications. It would require re-engineering the application and a separate paid database, at a

higher cost (~RM330–560/month). Not pursued.

## 4. Cost Comparison

### Cloud VPS (Shinjiru, 36-month term, prices exclude 8% SST)

| Plan | Specification | Monthly |
| --- | --- | --- |
| VALUE | 2 vCPU / 2 GB / 50 GB | RM27.90 |
| PRO | 4 vCPU / 4 GB / 100 GB | RM56.90 |
| PREMIUM | 6 vCPU / 6 GB / 150 GB | RM115.90 |

Plans can be upgraded seamlessly at any time (no migration, cost prorated), so we can start

small and scale up as the workload grows.

### On-Premise Server (one-time purchase)

| Item | Estimated Cost |
| --- | --- |
| Tower server (8-core, 32 GB ECC RAM, RAID-1 NVMe SSD) | ~RM12,000 |
| Windows Server 2022 Standard license (covers both VMs) | ~RM4,500 |
| UPS (battery backup) | ~RM2,000 |
| Backup storage (NAS) | ~RM3,000 |
| Total upfront | ~RM21,500 |
| Electricity (running 24/7) | ~RM900 / year |

### Total Cost of Ownership

| Option | 3-Year Total | 5-Year Total |
| --- | --- | --- |
| On-premise server (Prod + Test) | ~RM24,200 | ~RM26,000 |
| VPS PREMIUM + VALUE (Prod + Test) | ~RM5,600 | ~RM9,300 |
| VPS PREMIUM only (Prod) | ~RM4,500 | ~RM7,500 |

Observation: The cloud VPS is significantly cheaper in absolute terms over any realistic

horizon. An on-premise server only "breaks even" against the VPS after roughly 7–9 years — by which

time the hardware would need replacing. On-premise's value lies in **data control, in-house

ownership, and network-speed access**, not cost savings.

## 5. Recommended Plan — Phased Approach

### Phase 1 — Now through go-live (Development & UAT)

Subscribe to a cloud VPS, starting with the VALUE plan (~RM28/month).

Upgrade to PRO or PREMIUM as testing intensifies near go-live (upgrade is seamless).

Benefits: immediate, reliable hosted environment; no capital outlay; full flexibility while

requirements are still evolving; far superior to the current desktop PC.

### Phase 2 — At go-live (~2027)

With real, measured usage data (member volume, concurrent users, data growth), decide between:

(a) Purchasing a dedicated on-premise server (~RM21,500) to host Production and Test as two

virtual machines. This also permanently replaces the inadequate test PC and keeps all data

in-house; or

(b) Continuing on the cloud VPS if it is performing well and lower cost is preferred.

### Why phased?

Avoids spending ~RM21,500 on hardware before the system's true requirements are known.

Provides a proper hosted environment now, cheaply.

Preserves full flexibility — we commit capital only when we can size the hardware correctly.

## 6. Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| Member data (PII) hosted with a third party (VPS phase) | Reputable Malaysian provider; migrate to on-premise in Phase 2 if data-sovereignty is required |
| Single server hosting both Prod & Test (on-premise option) = single point of failure | Mandatory nightly database backup copied off-site; UPS protection |
| Long-term contract lock-in (VPS 36-month term) | Start with the low-cost VALUE plan; upgrades are seamless and prorated |
| Hardware failure / maintenance (on-premise) | Handled by in-house IT staff; hardware under manufacturer warranty; RAID-1 disk redundancy |

## 7. Recommendation & Approval Requested

We recommend approval to proceed with Phase 1: subscribe to a cloud VPS for development and UAT,

beginning at approximately RM28/month (VALUE plan), with the ability to upgrade as the system

approaches go-live.

The Phase 2 decision (on-premise server vs. continued VPS) will be brought back for approval

closer to go-live (~2027), supported by actual usage data and a firm hardware quotation.

Estimated Phase 1 commitment: ~RM28–116/month (scales with need).

Estimated Phase 2 capital (if on-premise approved): ~RM21,500 one-time.

*Prepared for management review. Figures are estimates based on current vendor quotations

(Shinjiru Technology) and prevailing hardware prices; final costs to be confirmed at time of

purchase. All VPS prices exclude 8% SST.*